## Sheet1
Sprint 0 (1 week)
9th March - 20th March | Scrum Events: - Product Vision: Defining and understanding the project. - Backlog Creation: Writing User Stories and PBIs. You will complete the important PBIs first. Leave the less important PBIs to be specify during the Sprints when you are free. - Backlog grooming Technical Tasks: - Initialize Spring Boot project, UI project, and Git repository. - Setup the Kanban board - Technical readiness
Sprint 1 (2 weeks)
23rd March (3 hours) | Sprint Planning: - Select PBIs to be develop within Sprint 1. - For each selected PBI, decompose the PBI into specific tasks and allocate developer(s) for the tasks. - Generate a Sprint Backlog
23rd March - 27 March before noon | Sprint Execution: - Start the software development. - Conduct Daily Scrum. - Join PBI Grooming as and when require.
3rd April 2 hours afternoon | Sprint Review
3rd April 2 hours afternoon | Sprint Retrospective
Sprint 2 (2 weeks)