## Sprint Summary
Sprint Summary
Sprint | Period | PBI Count | Non-PBI Count | Sprint Goal | Main Modules | Main Owners | Status
Sprint 1 | 28 March 2026 - 7 April 2026 | 9 | 4 | Complete the project foundation, authentication, profile features, and basic teacher project publishing capabilities | Authentication, Profile, Project Management, Engineering Support, Quality Assurance, Acceptance | ALL | Done
Sprint 2 | 8 April 2026 - 18 April 2026 | 9 | 4 | Complete project management, basic admin management, and student browsing/search entry points | Project Management, Admin, Student Project Browsing, Search, Quality Assurance, Acceptance | ALL | Done
Sprint 3 | 19 April 2026 - 29 April 2026 | 9 | 4 | Complete the main student search, filtering, application submission, review, and withdrawal workflow | Student Project Browsing, Application, Search, Project Management, Quality Assurance, Acceptance | ALL | Done
Sprint 4 | 30 April 2026 - 10 May 2026 | 18 | 4 | Complete teacher review, allocation consistency, status tracking, audit trail, and final quality closure | Notification, Application, Teacher Review, Allocation, Tracking, Admin, Project Management, Quality Assurance, Acceptance | ALL | Done

## Full Backlog
Sprint Overview (28 March 2026 - 10 May 2026)
Sprint | Owner | Item Type | PBI / Task | Title | Module | Priority | Completion Period | Status
Sprint 1 | Qi Chen | PBI | PBI 1.5 | Secure User Authentication and Access Control | Authentication | High | 28 March 2026 - 31 March 2026 | Done
Sprint 1 | Qi Chen | PBI | PBI 1.1 | User Registration and Login Interface | Authentication | High | 28 March 2026 - 30 March 2026 | Done
Sprint 1 | Qi Chen | PBI | PBI 1.2 | Role-based Homepage Redirection | Authentication | High | 31 March 2026 - 2 April 2026 | Done
Sprint 1 | Qi Chen | PBI | PBI 1.3 | Password Validation and Session Management | Authentication | High | 3 April 2026 - 5 April 2026 | Done
Sprint 1 | Zichen Fan | PBI | PBI 2.1 | Revise Personal Profile | Profile | High | 31 March 2026 - 3 April 2026 | Done
Sprint 1 | Zichen Fan | PBI | PBI 2.2 | Upload and Update Student Profile Information | Profile | Medium | 4 April 2026 - 6 April 2026 | Done
Sprint 1 | Zichen Fan | PBI | PBI 2.3 | View Teacher and Student Basic Information | Profile | Medium | 5 April 2026 - 7 April 2026 | Done
Sprint 1 | Wenjie Chen | PBI | PBI 3.1 | Teacher Project Creation Workflow | Project Management | High | 30 March 2026 - 4 April 2026 | Done
Sprint 1 | Wenjie Chen | PBI | PBI 3.5 | Teacher View of Own Published Projects | Project Management | Medium | 5 April 2026 - 7 April 2026 | Done
Sprint 2 | Wenjie Chen | PBI | PBI 3.2 | Teacher Project Editing and Updating | Project Management | High | 8 April 2026 - 11 April 2026 | Done
Sprint 2 | Wenjie Chen | PBI | PBI 3.3 | Teacher Project Deletion or Archiving | Project Management | Medium | 12 April 2026 - 14 April 2026 | Done
Sprint 2 | Wenjie Chen | PBI | PBI 3.4 | Project Form Validation and Error Feedback | Project Management | Medium | 15 April 2026 - 18 April 2026 | Done
Sprint 2 | Jianlin Zeng | PBI | PBI 4.1 | Admin User Management Dashboard | Admin | High | 8 April 2026 - 11 April 2026 | Done
Sprint 2 | Jianlin Zeng | PBI | PBI 4.2 | Admin Project Management and Moderation | Admin | High | 12 April 2026 - 15 April 2026 | Done
Sprint 2 | Jianlin Zeng | PBI | PBI 4.3 | Admin Approval of Teacher-submitted Projects | Admin | High | 16 April 2026 - 18 April 2026 | Done
Sprint 2 | Pingsong Deng | PBI | PBI 5.1 | Browse Project List with Responsive Pagination | Student Project Browsing | High | 8 April 2026 - 13 April 2026 | Done
Sprint 2 | Ziyi Jia | PBI | PBI 5.2 | Search for Projects Using Keywords | Student Project Browsing | High | 12 April 2026 - 16 April 2026 | Done
Sprint 2 | Shengyang Yin | PBI | PBI 5.3 | Backend Search Relevance Improvement Using Fuzzy Matching / Relevance Scoring | Search | Medium | 14 April 2026 - 18 April 2026 | Done
Sprint 3 | Ziyi Jia | PBI | PBI 5.4 | Filter Projects by Supervisor, Topic Area, or Availability | Student Project Browsing | High | 19 April 2026 - 22 April 2026 | Done
Sprint 3 | Pingsong Deng | PBI | PBI 5.5 | Submit and Review Project Applications | Application | High | 19 April 2026 - 24 April 2026 | Done
Sprint 3 | Pingsong Deng | PBI | PBI 5.6 | Project Detail Page Display | Student Project Browsing | Medium | 21 April 2026 - 24 April 2026 | Done
Sprint 3 | Pingsong Deng | PBI | PBI 5.7 | Student Application Confirmation Page | Application | Medium | 24 April 2026 - 26 April 2026 | Done
Sprint 3 | Shengyang Yin | PBI | PBI 5.8 | Backend Project Filtering by Category and Supervisor | Search | Medium | 22 April 2026 - 26 April 2026 | Done
Sprint 3 | Ziyi Jia | PBI | PBI 5.9 | Save Favourite Projects for Later Review | Student Project Browsing | Low | 25 April 2026 - 27 April 2026 | Done
Sprint 3 | Ziyi Jia | PBI | PBI 5.10 | View Recommended Projects Based on Search Keywords | Search | Low | 26 April 2026 - 28 April 2026 | Done
Sprint 3 | Qi Chen | PBI | PBI 6.1 | Project Request Submission Workflow | Application | High | 23 April 2026 - 28 April 2026 | Done
Sprint 3 | Chenrui Zhu | PBI | PBI 6.2 | Student Application Withdrawal and Project Availability Re-synchronisation | Application | High | 25 April 2026 - 29 April 2026 | Done
Sprint 4 | Chenrui Zhu | PBI | PBI 6.3 | Student Application Status Notification | Notification | Medium | 30 April 2026 - 2 May 2026 | Done
Sprint 4 | Pingsong Deng | PBI | PBI 6.4 | Limit Maximum Number of Active Applications | Application | High | 30 April 2026 - 3 May 2026 | Done
Sprint 4 | Ziyi Jia | PBI | PBI 6.5 | Display Submitted Application Summary to Students | Application | Medium | 1 May 2026 - 3 May 2026 | Done
Sprint 4 | Chenrui Zhu | PBI | PBI 7.1 | Teacher Application Queue and Applicant Context Viewing | Teacher Review | High | 30 April 2026 - 4 May 2026 | Done
Sprint 4 | Tianchen Niu | PBI | PBI 7.2 | Teacher Application Review and Decision Recording | Teacher Review | High | 2 May 2026 - 5 May 2026 | Done
Sprint 4 | Tianchen Niu | PBI | PBI 7.3 | Allocation Consistency and Audit Trail After Approval | Allocation | High | 4 May 2026 - 6 May 2026 | Done
Sprint 4 | Chenrui Zhu | PBI | PBI 7.4 | Teacher Applicant Filtering and Sorting | Teacher Review | Medium | 4 May 2026 - 6 May 2026 | Done
Sprint 4 | Tianchen Niu | PBI | PBI 7.5 | Teacher Rejection Reason Recording | Teacher Review | Medium | 5 May 2026 - 7 May 2026 | Done
Sprint 4 | Shengyang Yin | PBI | PBI 8.1 | Allocation Control with Backend Invalid-request Prevention and State Updates | Allocation | High | 3 May 2026 - 6 May 2026 | Done
Sprint 4 | Tianchen Niu | PBI | PBI 8.2 | Prevent Duplicate Allocation Results | Allocation | High | 6 May 2026 - 8 May 2026 | Done
Sprint 4 | Chenrui Zhu | PBI | PBI 8.3 | Project Capacity Update After Allocation Changes | Allocation | Medium | 6 May 2026 - 8 May 2026 | Done
Sprint 4 | Shengyang Yin | PBI | PBI 8.4 | Automatic Update of Project Availability Status | Allocation | Medium | 6 May 2026 - 9 May 2026 | Done
Sprint 4 | Shengyang Yin | PBI | PBI 8.5 | Backend Validation for Project Capacity Constraints | Allocation | Medium | 7 May 2026 - 9 May 2026 | Done
Sprint 4 | Zichen Fan | PBI | PBI 9.1 | Track Overview Status of Applications | Tracking | High | 3 May 2026 - 7 May 2026 | Done
Sprint 4 | Zichen Fan | PBI | PBI 9.2 | Application Progress Timeline Display | Tracking | Medium | 7 May 2026 - 9 May 2026 | Done
Sprint 4 | Tianchen Niu | PBI | PBI 9.3 | Admin Review of Allocation History | Admin | Medium | 7 May 2026 - 9 May 2026 | Done
Sprint 4 | Jianlin Zeng | PBI | PBI 4.4 | Admin System Data Overview Dashboard | Admin | Medium | 4 May 2026 - 8 May 2026 | Done
Sprint 4 | Jianlin Zeng | PBI | PBI 4.5 | Admin Audit Log Viewing and Export | Admin | Medium | 8 May 2026 - 10 May 2026 | Done
Sprint 1 | All | Non-PBI | Non-PBI | Sprint Planning and Sprint Backlog Confirmation | Project Management | High | 28 March 2026 | Done
Sprint 1 | Chenrui Zhu + Qi Chen | Non-PBI | Non-PBI | Environment Setup and Initial Integration Check | Engineering Support | High | 29 March 2026 - 30 March 2026 | Done
Sprint 1 | Zichen Fan + Wenjie Chen | Non-PBI | Non-PBI | Sprint 1 Quality Testing and Smoke Test | Quality Assurance | Medium | 6 April 2026 - 7 April 2026 | Done
Sprint 1 | Pingsong Deng + Shengyang Yin | Non-PBI | Non-PBI | Sprint 1 Review and Acceptance Preparation | Acceptance | Medium | 7 April 2026 | Done
Sprint 2 | All | Non-PBI | Non-PBI | Sprint Planning and Scope Reconfirmation | Project Management | High | 8 April 2026 | Done
Sprint 2 | Ziyi Jia + Jianlin Zeng | Non-PBI | Non-PBI | Frontend and Backend Integration Testing | Quality Assurance | Medium | 15 April 2026 - 16 April 2026 | Done
Sprint 2 | Tianchen Niu + Pingsong Deng | Non-PBI | Non-PBI | Sprint 2 Feature Test Submission | Quality Assurance | Medium | 17 April 2026 | Done
Sprint 2 | Wenjie Chen + Shengyang Yin | Non-PBI | Non-PBI | Sprint 2 Review, Bug Fixing, and Acceptance | Acceptance | Medium | 18 April 2026 | Done
Sprint 3 | All | Non-PBI | Non-PBI | Sprint Planning and User Flow Walkthrough | Project Management | High | 19 April 2026 | Done
Sprint 3 | Qi Chen + Chenrui Zhu | Non-PBI | Non-PBI | Application Workflow Integration Test | Quality Assurance | High | 26 April 2026 - 27 April 2026 | Done
Sprint 3 | Zichen Fan + Tianchen Niu | Non-PBI | Non-PBI | Regression Testing for Student-side Features | Quality Assurance | Medium | 28 April 2026 | Done
Sprint 3 | Pingsong Deng + Ziyi Jia | Non-PBI | Non-PBI | Sprint 3 Demo and Acceptance Review | Acceptance | Medium | 29 April 2026 | Done
Sprint 4 | All | Non-PBI | Non-PBI | Final Sprint Planning and Release Scope Lock | Project Management | High | 30 April 2026 | Done
Sprint 4 | Shengyang yin + Tianchen Niu | Non-PBI | Non-PBI | Allocation and Audit Trail Integration Testing | Quality Assurance | High | 6 May 2026 - 7 May 2026 | Done
Sprint 4 | Jianlin Zeng + Zichen Fan | Non-PBI | Non-PBI | System-wide Regression Testing and Test Submission | Quality Assurance | High | 8 May 2026 - 9 May 2026 | Done
Sprint 4 | Qi Chen + Wenjie Chen | Non-PBI | Non-PBI | Final Acceptance, Sprint Review, and Retrospective | Acceptance | High | 10 May 2026 | Done

## Sprint 1
Sprint 1 Sprint Plan (28 March 2026 - 7 April 2026)
Sprint Goal: Complete the project foundation, authentication, profile features, and basic teacher project publishing capabilities
Sprint | Owner | Item Type | PBI / Task | Title | Module | Priority | Completion Period | Status
Sprint 1 | Qi Chen | PBI | PBI 1.5 | Secure User Authentication and Access Control | Authentication | High | 28 March 2026 - 31 March 2026 | Done
Sprint 1 | Qi Chen | PBI | PBI 1.1 | User Registration and Login Interface | Authentication | High | 28 March 2026 - 30 March 2026 | Done
Sprint 1 | Qi Chen | PBI | PBI 1.2 | Role-based Homepage Redirection | Authentication | High | 31 March 2026 - 2 April 2026 | Done
Sprint 1 | Qi Chen | PBI | PBI 1.3 | Password Validation and Session Management | Authentication | High | 3 April 2026 - 5 April 2026 | Done
Sprint 1 | Zichen Fan | PBI | PBI 2.1 | Revise Personal Profile | Profile | High | 31 March 2026 - 3 April 2026 | Done
Sprint 1 | Zichen Fan | PBI | PBI 2.2 | Upload and Update Student Profile Information | Profile | Medium | 4 April 2026 - 6 April 2026 | Done
Sprint 1 | Zichen Fan | PBI | PBI 2.3 | View Teacher and Student Basic Information | Profile | Medium | 5 April 2026 - 7 April 2026 | Done
Sprint 1 | Wenjie Chen | PBI | PBI 3.1 | Teacher Project Creation Workflow | Project Management | High | 30 March 2026 - 4 April 2026 | Done
Sprint 1 | Wenjie Chen | PBI | PBI 3.5 | Teacher View of Own Published Projects | Project Management | Medium | 5 April 2026 - 7 April 2026 | Done
Sprint 1 | All | Non-PBI | Non-PBI | Sprint Planning and Sprint Backlog Confirmation | Project Management | High | 28 March 2026 | Done
Sprint 1 | Chenrui Zhu + Qi Chen | Non-PBI | Non-PBI | Environment Setup and Initial Integration Check | Engineering Support | High | 29 March 2026 - 30 March 2026 | Done
Sprint 1 | Zichen Fan + Wenjie Chen | Non-PBI | Non-PBI | Sprint 1 Quality Testing and Smoke Test | Quality Assurance | Medium | 6 April 2026 - 7 April 2026 | Done
Sprint 1 | Pingsong Deng + Shengyang Yin | Non-PBI | Non-PBI | Sprint 1 Review and Acceptance Preparation | Acceptance | Medium | 7 April 2026 | Done

## Sprint 2
Sprint 2 Sprint Plan (8 April 2026 - 18 April 2026)
Sprint Goal: Complete project management, basic admin management, and student browsing/search entry points
Sprint | Owner | Item Type | PBI / Task | Title | Module | Priority | Completion Period | Status
Sprint 2 | Wenjie Chen | PBI | PBI 3.2 | Teacher Project Editing and Updating | Project Management | High | 8 April 2026 - 11 April 2026 | Done
Sprint 2 | Wenjie Chen | PBI | PBI 3.3 | Teacher Project Deletion or Archiving | Project Management | Medium | 12 April 2026 - 14 April 2026 | Done
Sprint 2 | Wenjie Chen | PBI | PBI 3.4 | Project Form Validation and Error Feedback | Project Management | Medium | 15 April 2026 - 18 April 2026 | Done
Sprint 2 | Jianlin Zeng | PBI | PBI 4.1 | Admin User Management Dashboard | Admin | High | 8 April 2026 - 11 April 2026 | Done
Sprint 2 | Jianlin Zeng | PBI | PBI 4.2 | Admin Project Management and Moderation | Admin | High | 12 April 2026 - 15 April 2026 | Done
Sprint 2 | Jianlin Zeng | PBI | PBI 4.3 | Admin Approval of Teacher-submitted Projects | Admin | High | 16 April 2026 - 18 April 2026 | Done
Sprint 2 | Pingsong Deng | PBI | PBI 5.1 | Browse Project List with Responsive Pagination | Student Project Browsing | High | 8 April 2026 - 13 April 2026 | Done
Sprint 2 | Ziyi Jia | PBI | PBI 5.2 | Search for Projects Using Keywords | Student Project Browsing | High | 12 April 2026 - 16 April 2026 | Done
Sprint 2 | Shengyang Yin | PBI | PBI 5.3 | Backend Search Relevance Improvement Using Fuzzy Matching / Relevance Scoring | Search | Medium | 14 April 2026 - 18 April 2026 | Done
Sprint 2 | All | Non-PBI | Non-PBI | Sprint Planning and Scope Reconfirmation | Project Management | High | 8 April 2026 | Done
Sprint 2 | Ziyi Jia + Jianlin Zeng | Non-PBI | Non-PBI | Frontend and Backend Integration Testing | Quality Assurance | Medium | 15 April 2026 - 16 April 2026 | Done
Sprint 2 | Tianchen Niu + Pingsong Deng | Non-PBI | Non-PBI | Sprint 2 Feature Test Submission | Quality Assurance | Medium | 17 April 2026 | Done
Sprint 2 | Wenjie Chen + Shengyang Yin | Non-PBI | Non-PBI | Sprint 2 Review, Bug Fixing, and Acceptance | Acceptance | Medium | 18 April 2026 | Done

## Sprint 3
Sprint 3 Sprint Plan （19 April 2026 - 29 April 2026）
Sprint Goal: Complete the main student search, filtering, application submission, review, and withdrawal workflow
Sprint | Owner | Item Type | PBI / Task | Title | Module | Priority | Completion Period | Status
Sprint 3 | Ziyi Jia | PBI | PBI 5.4 | Filter Projects by Supervisor, Topic Area, or Availability | Student Project Browsing | High | 19 April 2026 - 22 April 2026 | Done
Sprint 3 | Pingsong Deng | PBI | PBI 5.5 | Submit and Review Project Applications | Application | High | 19 April 2026 - 24 April 2026 | Done
Sprint 3 | Pingsong Deng | PBI | PBI 5.6 | Project Detail Page Display | Student Project Browsing | Medium | 21 April 2026 - 24 April 2026 | Done
Sprint 3 | Pingsong Deng | PBI | PBI 5.7 | Student Application Confirmation Page | Application | Medium | 24 April 2026 - 26 April 2026 | Done
Sprint 3 | Shengyang Yin | PBI | PBI 5.8 | Backend Project Filtering by Category and Supervisor | Search | Medium | 22 April 2026 - 26 April 2026 | Done
Sprint 3 | Ziyi Jia | PBI | PBI 5.9 | Save Favourite Projects for Later Review | Student Project Browsing | Low | 25 April 2026 - 27 April 2026 | Done
Sprint 3 | Ziyi Jia | PBI | PBI 5.10 | View Recommended Projects Based on Search Keywords | Search | Low | 26 April 2026 - 28 April 2026 | Done
Sprint 3 | Qi Chen | PBI | PBI 6.1 | Project Request Submission Workflow | Application | High | 23 April 2026 - 28 April 2026 | Done
Sprint 3 | Chenrui Zhu | PBI | PBI 6.2 | Student Application Withdrawal and Project Availability Re-synchronisation | Application | High | 25 April 2026 - 29 April 2026 | Done
Sprint 3 | All | Non-PBI | Non-PBI | Sprint Planning and User Flow Walkthrough | Project Management | High | 19 April 2026 | Done
Sprint 3 | Qi Chen + Chenrui Zhu | Non-PBI | Non-PBI | Application Workflow Integration Test | Quality Assurance | High | 26 April 2026 - 27 April 2026 | Done
Sprint 3 | Zichen Fan + Tianchen Niu | Non-PBI | Non-PBI | Regression Testing for Student-side Features | Quality Assurance | Medium | 28 April 2026 | Done
Sprint 3 | Pingsong Deng + Ziyi Jia | Non-PBI | Non-PBI | Sprint 3 Demo and Acceptance Review | Acceptance | Medium | 29 April 2026 | Done

## Sprint 4
Sprint 4 Sprint Plan （30 April 2026 - 10 May 2026）
Sprint Goal: Complete teacher review, allocation consistency, status tracking, audit trail, and final quality closure
Sprint | Owner | Item Type | PBI / Task | Title | Module | Priority | Completion Period | Status
Sprint 4 | Chenrui Zhu | PBI | PBI 6.3 | Student Application Status Notification | Notification | Medium | 30 April 2026 - 2 May 2026 | Done
Sprint 4 | Pingsong Deng | PBI | PBI 6.4 | Limit Maximum Number of Active Applications | Application | High | 30 April 2026 - 3 May 2026 | Done
Sprint 4 | Ziyi Jia | PBI | PBI 6.5 | Display Submitted Application Summary to Students | Application | Medium | 1 May 2026 - 3 May 2026 | Done
Sprint 4 | Chenrui Zhu | PBI | PBI 7.1 | Teacher Application Queue and Applicant Context Viewing | Teacher Review | High | 30 April 2026 - 4 May 2026 | Done
Sprint 4 | Tianchen Niu | PBI | PBI 7.2 | Teacher Application Review and Decision Recording | Teacher Review | High | 2 May 2026 - 5 May 2026 | Done
Sprint 4 | Tianchen Niu | PBI | PBI 7.3 | Allocation Consistency and Audit Trail After Approval | Allocation | High | 4 May 2026 - 6 May 2026 | Done
Sprint 4 | Chenrui Zhu | PBI | PBI 7.4 | Teacher Applicant Filtering and Sorting | Teacher Review | Medium | 4 May 2026 - 6 May 2026 | Done
Sprint 4 | Tianchen Niu | PBI | PBI 7.5 | Teacher Rejection Reason Recording | Teacher Review | Medium | 5 May 2026 - 7 May 2026 | Done
Sprint 4 | Shengyang Yin | PBI | PBI 8.1 | Allocation Control with Backend Invalid-request Prevention and State Updates | Allocation | High | 3 May 2026 - 6 May 2026 | Done
Sprint 4 | Tianchen Niu | PBI | PBI 8.2 | Prevent Duplicate Allocation Results | Allocation | High | 6 May 2026 - 8 May 2026 | Done
Sprint 4 | Chenrui Zhu | PBI | PBI 8.3 | Project Capacity Update After Allocation Changes | Allocation | Medium | 6 May 2026 - 8 May 2026 | Done
Sprint 4 | Shengyang Yin | PBI | PBI 8.4 | Automatic Update of Project Availability Status | Allocation | Medium | 6 May 2026 - 9 May 2026 | Done
Sprint 4 | Shengyang Yin | PBI | PBI 8.5 | Backend Validation for Project Capacity Constraints | Allocation | Medium | 7 May 2026 - 9 May 2026 | Done
Sprint 4 | Zichen Fan | PBI | PBI 9.1 | Track Overview Status of Applications | Tracking | High | 3 May 2026 - 7 May 2026 | Done
Sprint 4 | Zichen Fan | PBI | PBI 9.2 | Application Progress Timeline Display | Tracking | Medium | 7 May 2026 - 9 May 2026 | Done
Sprint 4 | Tianchen Niu | PBI | PBI 9.3 | Admin Review of Allocation History | Admin | Medium | 7 May 2026 - 9 May 2026 | Done
Sprint 4 | Jianlin Zeng | PBI | PBI 4.4 | Admin System Data Overview Dashboard | Admin | Medium | 4 May 2026 - 8 May 2026 | Done
Sprint 4 | Jianlin Zeng | PBI | PBI 4.5 | Admin Audit Log Viewing and Export | Admin | Medium | 8 May 2026 - 10 May 2026 | Done
Sprint 4 | All | Non-PBI | Non-PBI | Final Sprint Planning and Release Scope Lock | Project Management | High | 30 April 2026 | Done
Sprint 4 | Shengyang Yin + Tianchen Niu | Non-PBI | Non-PBI | Allocation and Audit Trail Integration Testing | Quality Assurance | High | 6 May 2026 - 7 May 2026 | Done
Sprint 4 | Jianlin Zeng + Zichen Fan | Non-PBI | Non-PBI | System-wide Regression Testing and Test Submission | Quality Assurance | High | 8 May 2026 - 9 May 2026 | Done
Sprint 4 | Qi Chen + Wenjie Chen | Non-PBI | Non-PBI | Final Acceptance, Sprint Review, and Retrospective | Acceptance | High | 10 May 2026 | Done

## Owner Workload
Owner PBI Workload Check
Owner | PBI Count | Non-PBI Participation | Assigned Sprints
Qi Chen | 5 | 7 | Sprint 1, Sprint 3
Wenjie Chen | 5 | 7 | Sprint 1, Sprint 2
Pingsong Deng | 5 | 7 | Sprint 2, Sprint 3, Sprint 4
Zichen Fan | 5 | 7 | Sprint 1, Sprint 4
Ziyi Jia | 5 | 6 | Sprint 2, Sprint 3, Sprint 4
Tianchen Niu | 5 | 7 | Sprint 4
Shengyang Yin | 5 | 7 | Sprint 2, Sprint 3, Sprint 4
Chenrui Zhu | 5 | 6 | Sprint 3, Sprint 4
Jianlin Zeng | 5 | 6 | Sprint 2, Sprint 4